## kitchen
section | id | depends_on | start | end | deadline | est_duration | status | resource | task | progress | comments | microtasks | now
0_prep |  |  | TODAY |  |  | 1 | unscheduled | I | measure kitchen | 0
0_prep | roughplan | PREVIOUS |  |  |  | 2 | unscheduled | I | make a rough plan | 0
0_prep |  |  | PREVIOUS |  |  | 2 | unscheduled | I, F1, F2 | ask friends which companies they can recommend | 0 | Yyyy-mm-dd: .ask-for-XYZ: The company XYZ has opened a new store here. Should try to find if someone has experience with them. | .ask-for-XYZ
1_offer |  | PREVIOUS, roughplan |  |  |  | 5 | unscheduled | I, Company | make appointment with company for planning | 0
1_offer | plan | PREVIOUS |  |  |  | 1 | unscheduled | I, Company | plan new kitchen | 0
1_offer | buy | PREVIOUS |  |  |  | 1 | unscheduled | I | buy new kitchen | 0
2_installation |  | plan |  |  |  | 1 | unscheduled | I | make appointment for installation | 0 |  | .get-written-confirmation
2_installation |  | PREVIOUS, buy |  |  | 2020-02-07 | 1 | unscheduled | I, Company | installation of the new kitchen | 0 |  | .check-fridge .check-oven .check-stove .check-drawers